## Cover Page
Estimation & Schedule
<yyyy/mm/dd>
<yyyy/mm/dd>
<yyyy/mm/dd>
<Project Name>
<x.x>
Project Name:
Project Code:
Version:
Create Date:
Start Date:
End Date:
<Project Code>
<yyyy/mm/dd>
Project Effort:
Hướng dẫn sử dụng:
- Các nội dung tô màu vàng hoặc chữ in nghiêng là ví dụ. Cần thay bằng nội dung phù hợp
- Các hộp Text màu vàng là hướng dẫn bằng tiếng Việt. Xóa ngay sau khi đã hiểu và điển đủ thông tin, trước khi Release

## Record Of Changes
Record of Changes
Effective Date | Change Item | A/M/D(*) | Reason | Change Description | Creator | Reviewer / Approver | New version
<YYYY/MM/DD> | Create Test Plan | A |  | Initial version
-

## 1_ Introduction
Introduction
The Test Plan outlines the scope, approach, resources, and schedule of all testing activities. It identifies the items and features to be tested; types of testing; resource equirements; and an approach to project management.
Identifier
ProjectCode_TestPlan
About Tested Item
Summarize the software items and software features to be tested. The need for each item and its history may be included.
Objectives
Test plan for the project should support the following objectives:
| · | To detail the activities required to prepare for and conduct the system test
| · | To communicate to all responsible parties the tasks that they are to perform and the schedule to be followed in performing the tasks
| · | To define the sources of the information used to prepare the plan
| · | To define the test tools and environment needed to conduct the system test
Background
Last year the XYZ Corporate Systems and Programming Department developed a new General Ledger System at the request of the Corporate Accounting Department. A request was made at the same time for a new corporate payroll system to be developed that would interface with the general ledger system. The Management Systems Review Committee approved the request for the payroll system in September of 19xx and named a corporate payroll system advisory group to decide on the system requirements. The group ﬁnished a Statement of Requirements (AP01-01) and a Preliminary Development Plan (AP01-02) in Decem-ber 19xx
Document Overview
Outline the main sections in this document, include:
| · | Section 1 - Introduction about the Project Testing Process
| · | Section 2 - Test Items
| · | Section 3 - Approach
| · | Section 4 - Define Pass/Fail/Suspension/Resumption Criterias
| · | Section 5 - Project Management
| · | Section 6 - Project Team
| · | Section 7 - Specify environmental requirements about software, hardware and others
| · | Section 8 - Delivery Schedule
| · | Approval
| · | The final section is appendix
Testing Strategy
For each level of testing, prepare a separate test plan with the following set of deliverables:
| · | Features to be tested
| · | Items to be tested
| · | Management and technical approach
| · | Milestones
| · | Pass / Fail criteria
| · | Purpose for testing
| · | Risks, assumptions, and constraints
| · | Roles and responsibilities
| · | Schedules
Scope
Describe the scope (i.e. parameters) for the test plan(s). Also, list any areas specifically excluded from the plans. Outline how scheduled and unscheduled updates to the Software Test Plan will be managed. This document covers a full systems test of the project. This includes operator and user procedures, as well as programs and job control. In addition to comprehensively testing multi program functionality, external interfaces, environment, performance and stability will also be evaluated. Description about Abnormal Test is also a part of this document.
Reference Material
| 1 | Word Order | : | ProjectCode_WorkOrder_Vx.x_YYYYMMDD.doc
| 2 | Project Plan | : | ProjectCode_Estimation&Schedule_Vx.x_YYYYMMDD.xls
| 3 | Configuration Management Plan | : | ProjectCode_CM Plan_Vx.x_YYYYMMDD.doc
| 4 | Software Requirement Specification | : | ProjectCode_SRS_Vx.x_YYYYMMDD.xls
| 5 | User Requirement Defination | : | ProjectCode_URD_Vx.x_YYYYMMDD.xls
ID định danh của tài liệu và là đơn nhất
Thường là mã tài liệu (Testcase là 0102...), nhưng hiện tại, công ty chỉ có mã dự án, không có mã tài liệu, nên có thể sử dụng tên tài liệu
Mô tả ngắn gọn về phần mềm, đối tượng được kiểm thử
Mục tiêu của Test Plan
1 Mô tả các hoạt động cần thiết để phục vụ test
2 Liên hệ với các bên liên quan để họ thực hiện và tiến hành theo schedule đã định
3 Xác định các nguồn thông tin để chuẩn bị test
4 Xác định các công cụ và môi trường test
Mô tả sơ lược các mục, sheet của tài liệu
Bối cảnh quá trình test
- Viết rằng đây là dự án đầu tiên
- Viết rằng đây là phiên bản step 2 của một dự án trước, được hoàn thành vào thời điểm nào, do ai quản lý
- Viết rằng dự án này thuộc dạng maintain nên test là nội dung chính của dự án
Chiến lược test
Cho biết, khi kế hoạch test lớn được chia thành các kế hoạch nhỏ, thì test plan của các kế hoạch nhỏ phải chứa các nội dung gì
Phạm vi kiểm thử
Mô tả phạm vi, tham số kiểm thử của quá trình kiểm thử. Liệt kê các vùng vĩ mô, chung chung nằm ngoài yêu cầu kiểm thử như: không test lại tính năng của version trước đó, không kiểm tra giao diện. Xem thêm Sheet Test Items, mục Feature Outside of Scope chỉ là tính năng cụ thể.
Xem tài liệu ED hoặc yêu cầu của khách hàng để điển. Có thể là giới hàn của hệ thống, ví dụ, chỉ test với 30 máy, chỉ hỗ trợ tối đa 30 kênh
Các tài liệu, nguồn thông tin để làm test plan, là cơ sở để xây dựng test plan. Thường là các tài liệu quản lý dự án, SRS, phân bổ nhân sự, CM Plan. Tùy dự án có thể thêm
- User Requirement Defination
Không chứa tài liệu liên quan tới việc kiểm thử cụ thể, không chứa tài liệu design.

## 2_ Test Items
Test Items
All items that make up the project {ProjectName} will be tested during the system test. The versions to be tested will be placed in the appropriate libraries by the conﬁguration administrator. The administrator will also control changes to the versions under test and notify the test group when new versions are available
Operation Documents
| 1 | Test Specification |  |  | : | ProjectCode_TestSpec_Vx.x_YYYYMMDD.doc
| 2 | Test Case |  |  | : | ProjectCode_TestCase_Vx.x_YYYYMMDD.doc
| 3 | Design specification |  |  | : | ProjectCode_ExternalDesign
| 4 | Design specification |  |  | : | ProjectCode_ExternalDesign
| 5 | Users guide |  |  | : | ProjectCode_UserGuide
| 6 | Installation guide |  |  |  | ProjectCode_InstallationGuide
Program Modules
| No. |  | Type |  | Package
| 1 |  | Source Code |  | ProjectCode_Source.zip
| 2 |  | Setup Package |  | ProjectCode_Setup.exe
Feature To Be Tested
| No. |  |  | Test Specification |  |  |  |  | Description
| 1 |  | ProjectCode_TestSpec_Security |  |  |  | Security
| 2 |  | ProjectCode_TestSpec_Recovery |  |  |  | Recovery
| 3 |  | ProjectCode_TestSpec / Sheet Performance |  |  |  | Performance
| 4 |  | ProjectCode_TestCase / Sheet General Users |  |  |  | Processing for general users
| 5 |  | ProjectCode_TestCase / Sheet Spec:Admin |  |  |  | Processing for administrator
Feature Not To Be Tested
The following features will not be included in the system tests because they are not to be used when the system is initially installed:
| 1 | Equal Employment Opportunity Commission Compliance Reports
| 2 | Internal Training Schedule Reports
The development Phase 2.0 documentation will contain a test plan for these features.
Identify why the feature is not to be tested, there can be any number of reasons.
Not to be included in this release of the Software.
Low risk, has been used before and was considered stable.
Will be released but not tested or documented as a functional part of the release of this version of the software.
| No. |  | Non Test Specification |  |  |  |  | Reason
| 1 |  | Only test with calling and play after calling immediately, exit Media Player. Not support Stop when playing, Play after stopped, minimizing activities, or any other activity of Media Player. |  |  |  |  | It is useless with the purpose of project
| 2 |  | Exceptions of Fields of Data Files, such as invalid value, out of range value,etc. Note that, Exceptions of Data File still be tested, such as no file, etc. |  |  |  |  | Data File is only read/written from the program by user according to XML standard. So user will not edit this file directly by some editor program. Exception of Fields only occur when writing process or someone edit this file manually. This case is very
3
4
5
6
7
8
Xác định các thành phần, chức năng và việc kết hợp thành phần chức năng sẽ được kiểm thử.
Dựa vào SRS để xác định các chức năng chính phải thực hiện
Xác định các thành phần, chức năng và việc kết hợp thành phần chức năng không được test trên cả 2 phương diện, kỹ thuật và người dùng cuối. Dựa vào SRS
Lý do thường bao gồm:
-Tính năng chưa có trong bản release hiện tại
-Rủi ro thấp, đã được sử dụng trước đây và coi như là chấp nhận được, ổn định
- Sẻ được release nhưng chưa được test hoặc ghi nhận là một chức năng của bản release hiện tại
- Các ngoại lệ với file cấu hình, file dữ liệu.. hoặc ngoại lệ với trường dữ liệu nào đó trong các file trên không cần kiểm tra do file dữ liệu theo chuẩn XML, không thể thay đổi tay, do chỉ có thể nhập liệu từ dialog,.. nên khả năng xảy ra ngoại lệ thấp.
Xem thêm Sheet Introduction, mục Scope
Các module do Dev gửi cho QA để thực hiện kiểm thử để chăc chắn rằng nội dung là chính xác. Đây chính là sản phẩm cần test
Có thể bao gồm các báo cáo nếu là sản phẩm cuối
Các tài liệu giúp xác định quá trình test, vạch ra các hoạt động kiểm thử

## 3_ Approach
Approach
Identify the different types of testing and the methods and criteria for performing the test activities. For each level of testing, prepare a test plan and the appropriate set of deliverables.
Unit Testing
Describe how Unit Testing will be conducted to verify the implementation of each software element or collection of software elements.
Intergration Testing - System Testing
Describe how Integration Testing will be conducted on software and hardware elements, until the entire system has been integrated. This ensures that the design objectives are met and that the software complies with operational requirements.
Conversion Testing
Elements (and historical data) are converted from the previous system format to the new system format
Interface Testing
Describe how Interface Testing will be conducted to ensure that the
application operates efficiently outside the application boundary.
Security Testing
Describe how Security Testing will be conducted so that the application
systems control and auditability features are functional
Recovery Testing
Describe how Recovery Testing will be conducted to ensure that the
application’s restart, backup, and recovery facilities operate as designed.
Performance Testing
Describe how Performance Testing will be conducted to ensure that the
application performs to customer expectations (e.g. response time).
Regression Testing
Describe how Regression Testing will be conducted to ensure that changes
to the application have not adversely affected previously tested functionality
Acceptance Testing
Describe how Acceptance Testing will be conducted to ensure that the
system satisfies the acceptance criteria.
Beta Testing
Describe how Beta Testing will be conducted to detect application faults,
failures, and defects.
Mô tả phương pháp, đường lối test. Với mỗi kiểu test hoặc test tích hợp,
- Chỉ rõ phương pháp và cách để xác định như thế nào là thành công (ví dụ 99% test ok là thành công, 98% test ok là chấp nhận được, 97% là thất bại, và chỉ delivery khi kết quả test >=98%).
- Đặc tả các hoạt động chính, các kỹ thuật và các công cụ tương ứng (Phải tham chiếu tới sheet Environmental Requirements, mục Tools)
- Phương pháp phải được mô tả một cách đầy đủ để làm cơ sở ước lượng thời gian cần test cho mỗi hạng mục.
- Số lượng testcase tối thiểu
- Số lượng lỗi tối thiểu phát hiện được với từng hạng mục. Ví dụ, phải tìm thấy ít nhất 10 lỗi với chức năng A.
- Các thông tin thông kê trước đây đã khảo sát được về số lượng lỗi của từng module.
- Bổ sung về sau, nếu trong quá trình test có vấn đề lạ phát sinh thì ghi chép vào đây để làm kinh nghiệm, ví dụ có một số kết quả test lạ thì xử lý thế nào trong trường hợp cụ thể

## 4_ Criterias
Criterias
Specify the criteria to be used to determine whether each test item has passed or failed testing.
Pass Criteria
The system must also satisfy the following requirements:
| · | Memory requirements must not be greater than 64K of real storage
| · | Consistency of user procedures with other systems must satisfy this product
Fail Criteria
Suspension Criteria
Inability to convert the Employee Information Database will cause suspension of
all testing activities
Resumption Criteria
When a new version of the system is transmitted to the test group after a
suspension of testing has occurred, a regression test as described in 6.7 will be run.
Các điều kiện để một test được coi là OK
- Giá trị đo thực tế trùng với giá trị mong đợi
- Thỏa mãn các điều kiện khác về bộ nhớ, CPU
- Không xung đột với một số phần mềm chỉ định
Các điều kiện để một test được coi là Fail
- Giá trị đo thực tế không với giá trị mong đợi
- Không thỏa mãn điều kiện khác về Mem, CPU
- Xung đột phần mềm
Các điều kiện để một test được coi là Tạm dừng
- Khi không ảnh hưởng tới hệ thống hiện tại, nhưng không tốt như mong muốn
- Khi khả năng xảy ra quá thấp (Nếu tình trạng này được dự kiến từ trước và đã thỏa thuận được với K.Hàng thì sẽ nằm trong Sheet Test Items, mục Feature Outof Scope)
Các điều kiện để một test được thực hiện lại
- Khi phiên bản mới được gửi tới.
- Khi thay đổi một số điều kiện nào đó về môi trường. Ví dụ OS, bộ xử lý...

## 5_ Test Management
Test Management
Test Deliverables
| 1 | Test Specification
| 2 | Test Item Transmittal Reports
| 3 | Test Incident Reports
| 4 | Test Sumary Report
| 5 | Test Input Data and Test Output Data
| 6 | Test Tool
Testing Task
| No |  | Task | Predecessor Tasks |  | Special skills | Responsibility | Effort | Finish Date
| 1 |  | Prepare test plan | Complete design description and preliminary development plan |  | Excel | QA | 4
2
3
4
5
Risk & Contigencies
Inability to convert the Employee Information Database will cause suspension of all testing activities
Identify the high-risk assumptions of the test plan:
| · | Specify contingency plans for each (e.g., delayed delivery of test items might require increased night shift scheduling to meet the delivery date)
| · | Example: If the testing schedule is significantly impacted by system failure, the development manager has agreed to assign a full-time person to the test group to do
debugging
| · | Example: If hardware problems impact system availability during the day, then the test group will schedule their activities during the evening or on Sunday
| · | Example: If the necessary resources are insufficient, the person who is responsible for project must report and get enough materials
Danh sách các tài liệu sẽ gửi Delivery liên quan tới quá trình kiểm thử
Liệt kê các nhiệm vụ cần thiết, các kỹ năng cần có để chuẩn bị và thực hiện test.
Những rủi ro có thể gặp phải và cách phòng tránh cũng như xử lý khi gặp phải

## 6_ Project Team
Project Team
Responsibilies
Developement Project Group:
This group transmits the system to be tested and responds to the System Test Incident Reports. This group does any program debugging that is required. It also supplies the database auditor. (See Estimate&Schedule document, section Resource Planned)
System Test Group
This group provides the overall management of the testing and the technical testing expertise.
(See Estimate&Schedule document, section Resource Planned, or following content)
Jobs Of Each Role
See Job Process RADIO document
Staffing and Training Needs
System Test Group
| No |  | Name | Role/Position | Contact Info |  | Start Date | End Date | Working Time |  | Qualification Information
| 1 |  |  | Supervisor |  |  | <YYYY/MM/DD> | <YYYY/MM/DD>
| 2 |  |  | QA |  |  | <YYYY/MM/DD> | <YYYY/MM/DD>
| 3 |  |  | PQA |  |  | <YYYY/MM/DD> | <YYYY/MM/DD>
| 4 |  |  | Tester |  |  | <YYYY/MM/DD> | <YYYY/MM/DD>
Trainning
| No |  | Skill | Role/Position | Resources |  |  |  | Start Date | End Date |  | Status
| 1 |  | Using Test Link | Tester1, QA | TestLink UserGuide, Learning Meeting |  |  |  | <YYYY/MM/DD> | <YYYY/MM/DD> |  | Not yet
| 2 |  | Using DMS | [5 empty] | <YYYY/MM/DD> | <YYYY/MM/DD>
| 3 | [7 empty] | <YYYY/MM/DD> | <YYYY/MM/DD>
| 4 | [7 empty] | <YYYY/MM/DD> | <YYYY/MM/DD>
| 5 | [7 empty] | <YYYY/MM/DD> | <YYYY/MM/DD>
Vai trò của các cá nhân tham gia quá trình kiểm thử dự án.
Bảng này là một phần nội dung của tài liệu Estimate&Schedule / Sheet Resource & Planned
Bố sung thêm Supervisor: là người am hiểu mục đích thực của hệ thống, với những trường hợp test cho kết quả lạ thì phải hỏi Supervisor để quyết định Fail hay OK. Thông thường, Supervisor là khách hàng
Công việc cụ thể của từng vai trò
Luôn luôn xem, ánh xạ tới tài liệu Job Process RADIO
Các kỹ năng cần thiết và việc tập huấn kỹ năng cho các thành viên.
Mỗi kỹ năng Skill sẽ phải đào tạo cho một vài vị trí Position khác nhau. Tài nguyên có thể là tài liệu sử dụng tool (Xem mục Documents của Sheet Environmental Requirements), hoặc một khóa học ngăn hạn. QA quyết định thời gian học và cập nhật trường Status là Yes khi kết thúc
Mô tả vai trò nhiệm vụ test của từng nhóm dự án
Nhóm phát triển phần mềm - Codding có nhiệm vụ chuyển giao hệ thống cho bên QA và xử lý, giải quyết các lỗi phát hiện được. Nhóm này bao gồmProgrammer, Programer
Nhóm test hệ thống: Quản lý mọi vấn đề, kỹ thuật và kỹ thuật liên quan tới test

## 7_ Environmental Requirements
Environmental Requirements
Hardware
| 1. | Router AR450S
| 2. | At least 4 PCs have 2 network cards
Software
| 1. | Operating System:
|  |  | + | Windows XP, 2003
|  |  | + | Linux CentOS 4.x
| 2. | Database:
|  |  | + | PostgreSQL version 8.1.x or later
|  |  | + | Oracle 9i or later
Security
| - | No special requirement
| - | Security will be limited to existing controls
Tools
The following test tools are required to support systems testing:
| 1 | Web Application Stress
Microsoft's Web Application Stress Tool provides an easy way to simulate large numbers of users against your Web application. This tool makes it possible to make intelligent decisions about hardware and software load incurred by your application and how much traffic a given machine or group of machines can handle. In this article Rick shows how the tool works and how to properly interpret the performance data it generates
| 2 | Router Simulator
Router simulator is a simple program which executes the communication of master host with Router, follow a defined scenario. If use this simulator, you do not need Router to test Server Defense system. The difference with Serial_Port is Router Simulator contain multi states
| 3 | CPU Killer
To change the CPU Load exactly, affect the real performance of CPU
| 4 | Max CPU Killer
To change the CPU Load exactly, doesn’t affect the real performance of CPU
Documents
The following documents are required to support systems testing:
| - | Statement of Requirements
| - | Design Description
| - | User Guide
| - | Installationg Guide
| - | WAS_UserGuide
| - | Snort_UserGuide
| - | RouterSim_InstallationUserGuide
Danh sách các thiết bị phần cứng cần thiết để kiểm thử.
Danh sách các phần mềm cần thiết để chạy hệ thống. Các phần mềm này chỉ liên quan tới việc chạy hệ thống ở mức người dùng sản phẩm, không bao gồm các công cụ đặc biệt để hỗ trợ kiểm thử.
Yêu cầu về Security khi kiểm thử
Danh sách các công cụ đặc biệt để hỗ trợ kiểm thử.
Tài liệu liên quan tới việc xác lập môi trường kiểm thử. Ví dụ:
các hướng dẫn cài đặt, sử dụng hệ thống
hướng dẫn sử dụng test tool,
link download tool,
link hướng dẫn sử dụng tool,
tài liệu đặc tả về một số cấu hình mạng sử dụng để test, file nén chứa các file cấu hình của 1 cấu hình nào đó
PO
PS…..
PO
PS…..

## 8_ Delivery Schedule
Delivery Schedule
No | Deliverable | Description | Delivery date | Middle | Final | Delivery location | Document Reference | Note
|  |  | <YYYY/MM/DD> | O |  |  | <Patch of Release Note docs>
O

## Approval
Approval
Disclaimers
The information contained in this document is the proprietary and exclusive property of AI&T except as otherwise indicated. No part of this document, in whole or in part, may be reproduced, stored, transmitted, r used for design purposes without the prior written permission of AI&T. The information contained in this document is subject to change without notice. The information in this document is provided for informational purposes only. AI&T specifically disclaims all warranties, express or limited, including, but not limited, to the implied warranties of merchantability and fitness for a particular purpose, except as provided for in a separate software license agreement.
Privacy Information
This document may contain information of a sensitive nature. This information should not be given to persons other than those who are involved in the project or who will become involved during the lifecycle.
Document Owner
The primary contact for questions regarding this document is:
| Author | :
| Project Name | :
| Project Sign | :
| Phone | : | +84 4 7624015
| Email | :
Document Approval
| Test Manager |  |  |  | Date | Note:
| Project Leader |  |  |  | Date
| QA Manager |  |  |  | Date

## Appendix
Appendix
No | Term |  |  | Description
1 | design level | The design decomposition of the software item (e.g., system, subsystem, program, or module)
2 | pass/fail criteria | Decision rules used to determine whether a software item or a software feature passes or fails a test
3 | software feature | A distinguishing characteristic of a software item (e.g., performance, portability, or functionality)
4 | software item | Source code, object code, job control code, control data, or a collection of these items
5 | test | A set of one or more test cases, or A set of one or more test procedures, or A set of one or more test cases and procedures
6 | test case speciﬁcation | A document specifying inputs, predicted results, and a set of execution conditions for a test item
7 | test design speciﬁcation | A document specifying the details of the test approach for a software feature or combination of software features and identifying the associated tests
8 | test incident report | A document reporting on any event that occurs during the testing process which requires investigation
9 | testing | The process of analyzing a software item to detect the differences between existing and required conditions (that is, bugs) and to evaluate the features of the software item
10 | test item | A software item which is an object of testing
11 | test item transmittal report | A document identifying test items. It contains current status and location information
12 | test log | A chronological record of relevant details about the execution of tests
13 | test plan | A document describing the scope, approach, resources, and schedule of intended testing activities. It identiﬁes test items, the features to be tested, the testing tasks, who will do each task, and any risks requiring contingency planning
14 | test procedure speciﬁcation | A document specifying a sequence of actions for the execution of a test
15 | test summary report | A document summarizing testing activities and results. It also contains an evaluation of the corresponding test items